## Sheet1
Agile Story Point Startup Sheet |  |  | Todays Date
2018-12-11
Team Name | Project Name | [5 empty] | Start Date
TechMates | Tragen-Trucks | [5 empty] | 2018-10-18
Story Point Values
Team Member Name |  | Points | 1
NIDS |  | 22.5 | 2
RAHUL |  | 20.5 | 4
DISHA |  | 21 | 5 | Only change values in orange
MINNIE |  | 21 | 8
MUKUNTH |  | 20 | 13
|  | 0 | 16
32
|  | Projected |  |  | Points Allocated
Story or Tasks |  | Story Points | NIDS | RAHUL | DISHA | MINNIE | MUKUNTH | 0 | Total
Scrum master/facilitator/coordinator |  | 5 | 5 | [5 empty] | 5
Executive Summary |  | 2 |  |  |  | 2 | 0 |  | 2
Business overview |  | 5 | 2.5 | 2.5 |  |  |  |  | 5
Prototype development |  | 4 |  |  | 2 |  | 2 |  | 4
Competitive environment analysis |  | 2 | 1 | 1 |  |  |  |  | 2
Marketing strategy |  | 8 |  |  |  | 4 | 4 |  | 8
Operations strategy |  | 8 | 4 | 2 | 2 |  |  |  | 8
Human resources strategy |  | 5 | 1 | 1 | 1 | 1 | 1 |  | 5
Financials and forecasts |  | 8 |  |  | 4 | 4 |  |  | 8
Stage of development/implementation plan |  | 4 |  | 2 | 2 |  |  |  | 4
Angel, venture & private funding needed |  | 4 | 4 | [5 empty] | 4
Business plan Summary |  | 5 |  |  | 2 | 1 | 2 |  | 5
Integrating business plan material |  | 8 |  | 3 | 2 | 1 | 2 |  | 8
Integrating the material for the pitch |  | 13 |  | 3 |  | 5 | 5 |  | 13
Delivering the pitch |  | 16 | 5 | 4 | 4 | 1 | 2 |  | 16
Assembling final deliverables and transmitting |  | 8 | 0 | 2 | 2 | 2 | 2 |  | 8
Total |  | 105 | 22.5 | 20.5 | 21 | 21 | 20 | 0 | 105
Todays Date
Effort Expended as Reported by individual |  |  | 2018-12-11
Do this after you complete the project
|  | Projected |  |  | Points Used
Story or Tasks |  | Points | NIDS | RAHUL | DISHA | MINNIE | MUKUNTH | 0 | Total | % | Finished
Scrum master/facilitator/coordinator |  | 5 | 5 | [5 empty] | 5 | 100% | Y
Executive Summary |  | 2 |  |  |  | 2 |  |  | 2 | 100% | Y
Business overview |  | 5 | 2.5 | 2.5 |  |  |  |  | 5 | 100% | Y
Prototype development |  | 4 |  |  | 2 |  | 2 |  | 4 | 100% | Y
Competitive environment analysis |  | 2 | 1 | 1 |  |  |  |  | 2 | 100% | Y
Marketing strategy |  | 8 |  |  |  | 4 | 4 |  | 8 | 100% | Y
Operations strategy |  | 8 | 4 | 2 | 2 |  |  |  | 8 | 100% | Y
Human resources strategy |  | 5 | 1 | 1 | 1 | 1 | 1 |  | 5 | 100% | Y
Financials and forecasts |  | 8 |  |  | 4 | 4 |  |  | 8 | 100% | Y
Stage of development/implementation plan |  | 4 |  | 2 | 2 |  |  |  | 4 | 100% | Y
Angel, venture & private funding needed |  | 4 | 4 | [5 empty] | 4 | 100% | Y
Business plan Summary |  | 5 |  |  | 2 | 1 | 2 |  | 5 | 100% | Y
Integrating business plan material |  | 8 |  | 3 | 2 | 1 | 2 |  | 8 | 100% | Y
Integrating the material for the pitch |  | 13 |  | 3 |  | 5 | 5 |  | 13 | 100% | Y
Delivering the pitch |  | 16 | 5 | 4 | 4 | 1 | 2 |  | 16 | 100% | Y
Assembling final deliverables and transmitting |  | 10 | 2 | 2 | 2 | 2 | 2 |  | 10 | 100% | Y | Over Allocation
Total |  | 105 | 24.5 | 20.5 | 21 | 21 | 20 | 0 | 107 | 101.9% | Y
Work days into project |  | 39
Agile Velocity (AV=total effort/day) |  | 2.6923
AV per person (Agile Velocity/number) |  | 0.44872
Over Allocation | 2 Points